## Лист1
CCM non-government sector selection Action Plan 2018
# | Activities | Time frame | Responsible party
1 | Development and approval of the Terms of Reference for the conduct of selection (hereinafter - the Terms of Reference) to the Country Coordinating Committee on work with International Organizations on HIV and Tuberculosis issues (herinafter - the CCM) | July-August 2018 | CCM Secretariat
2 | Development and approval of the application forms for NGO representatives and application forms for individulas - communities' representatives | July-August 2018 | CCM Secretariat
3 | Establishment of the Mandate Commission | 20-30 August 2018 | CCM Secretariat
4 | Creation of an e-mail address for registration of applicants and constituencies | 30 September 2018 | CCM Secretariat
5 | Announcement of the start of selection process and submission of applications from national NGOs and people affected by diseases. Announcement is published using national media, CCM website, e-mails. | 1-5 October 2018 | CCM Secretariat
6 | Collection and registration of applications from candidates and constituencies - representatives of national NGOs and persons affected by diseases. A separate e-mail address is created, to which applications are sent, access is given to the Mandate Commission members | 8-31 October 2018 | CCM Secretariat Mandate Commission
7 | Registration of candidates from international NGOs and multilateral/bilateral development partners. International non-governmental organizations select their representatives through participation in transparent, officially documented selections at a forum of international NGOs in accordance with the established and approved procedures, developed within the constituency. | 8-31 October 2018 | CCM Secretariat
8 | Data collection and analysis, verification of submitted applications for compliance with the criteria of the Terms of Reference and transfer of the list of applicants to the CCM Secretariat. The Mandate Commission provides the CCM Secretariat with the Minutes on the results of registration of organizations and candidates. | 1-10 November 2018 | Mandate Commission | 0
9 | Compiling and publishing the list of potential CCM candidates for each constituency and the beginning of voting. | 12 November 2018 | CCM Secretariat
10 | Voting and counting of voting results. The Mandate Commission provides the CCM Secretariat with the Minutes on the voting results. | 13-15 November 2018 | Mandate Commission
11 | Publication of the voting results and submission of supporting documents to the CCM Secretariat. Publication of the voting results on the CCM website | 16-20 November2018 | CCM Secretariat
12 | Conducting an induction brieifing for newly selected CCM members | 20-30 November 2018 | CCM Secretariat
Amanzholov N.
CCM Vice-Chair
President, "Kazakh Union of People Living with HIV"
Goliusov A.
CCM Vice-Chair
Director, UNAIDS Office in Kazakhstan