## Oversight 2020
Approved by CCM decision on 31 January 2020
CCM Oversight Plan 2020
Project title: | Support to CCM for 2020-2022
Period: | 2020
Implementing partner: | CCM, MoH, UNDP
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Total expenditure 2020 | Responsible parties
|  | Q1 | Q2 | Q3 | Q4
Oversight activities completed with participation by all CCM constituencies (documented)
СКК Reports with recommendations of Oversight Committee presented to CCM and published on CCM web-site | 2020: Oversight visit to Karaganda region (5 days) will be conducted by 5 specialists to identify progress in implementation of TB and HIV Programmes that were earlier funded by GFATM. During the meeting with local authorities the State social orders for NGOs will be emphasized. Finance expert will not be involved since the GFATM Funding was not provided. | 7-11 September 2020 |  |  |  | 2958 | Oversight Committee, CCM, MoH, PR, SR
| Oversight visit to Nur-Sultan (4 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, participation in an advocacy meeting on OST |  |  |  |  | 4972
| Oversight visit to Mangystau region (4 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, participation in an advocacy meeting on OST |  |  |  |  | 4672
| Oversight visit to Pavlodar region (3 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, participation in an advocacy meeting on OST |  |  |  |  | 2576
| Oversight visit to North-Kazakhstan region (3 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, participation in an advocacy meeting on OST |  |  |  |  | 3016
Reports and presentations on the results of review are developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV component on the results of 2020, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting to be held in September 2020. |  | 6 April (TB) |  |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of PR determined on the results of the PUDR review |  | 20 April (HIV)
| Oversight Committee meeting to analyse the reports of PR for HIV component determined on the results of the Oversight visits review |  |  | 12 August | 27 November
| Oversight Committee meeting to analyse the reports of PR for TB component determined on the results of the Oversight visits review |  |  |  | 26 November
Minutes of the meetings, Declarations on Conflict of Interests are signed and published on CCM web-site | CCM meeting to be held in Nur-Sultan with participation of MoH, CCM. Both PRs and LFA take part in the meeting. Meeting agenda includes: 1) GF allocation for 2020-2022; approval of Program split; PR approval for HIV grant; approval of the Country Dialogue Plan; 2) approval of the HIV Funding Request for 2021-2023; 3) approval of the GF COVID-19 funding request etc. | 2020-01-31 | 2020-06-11 | 2020-08-07 |  | 10800 | Oversight Committee, CCM members and partners
| Meeting of CCM working groups with national partners (government organizations, NGOs and international organizations) | regularly | regularly | regularly | regularly | 300
| Meeting of CCM working groups with national partners (government organizations, NGOs and international organizations) | regularly | regularly | regularly | regularly | 300
| Electronic approvals involving two PRs and LFA. Materials will be presented that require approval of the CCM. | regularly | regularly | regularly | regularly
| Establishing platforms with MSM, SW, PWID, PLHIV communities | until 30 October |  |  |  |  | Oversight Committee, CCM, MoH, PR, SR
| Establishing platforms with MSM community | 2020-09-10
| Establishing platforms with SW community |  | upon agreement
| Establishing platforms with PWID community |  | upon agreement
| Establishing platforms with PLHIV community |  | upon agreement