## Oversight 2020
Approved on 1 December 2020
CCM Oversight Plan 2021
Project title: | Support to CCM for 2020-2022
Period: | 2021
Implementing partner: | CCM, MoH, UNDP, UNAIDS
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Total expenditure 2021 | Responsible parties
|  | Q1 | Q2 | Q3 | Q4
Oversight activities completed with participation by all CCM constituencies (documented)
Reports with recommendations of Oversight Committee presented to CCM and published on CCM web-site | 2021: Oversight visit to 4 regions (2 days) will be conducted by 6 specialists to identify progress in implementation of TB and HIV Programmes that were earlier funded by GFATM. During the meeting with local authorities the State social orders for NGOs will be emphasized. Finance expert will be involved. | [5 empty] | Oversight Committee, CCM, MoH, PR, SR
| Oversight visit to Atyrau region (2 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology Center, NGO |  |  |  |  | 3220
| Oversight visit to East-Kazakhstan region (2 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, NGO |  |  |  |  | 3000
| Oversight visit to Pavlodar region (2 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, NGO |  |  |  |  | 2660
| Oversight visit to Kostanay region (2 days): Regional AIDS Center, Regional TB Dispensary, Regional Narcology, NGO |  |  |  |  | 2660
Reports and presentations on the results of review are developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV components on the results of 2020, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting. |  | April (TB) |  |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of PR determined on the results of the PUDR review |  | April (HIV)
| Oversight Committee meeting to analyse the reports of PR for HIV component determined on the results of the Oversight visits review |  |  | August | November
| Oversight Committee meeting to analyse the reports of PR for TB component determined on the results of the Oversight visits review |  |  |  | November
Minutes of the meetings, Declarations on Conflict of Interests are signed and published on CCM web-site | CCM meeting to be held in Nur-Sultan with participation of MoH, CCM. Both PRs and LFA take part in the meeting. Meeting agenda includes: 1) Launch of the Global Fund grant ; 2) presentations of key populations 3) approval of the multycountry funding request; 4) Activites on HIV and TB prevention programs. | 2021-02-03 | 2021-04-04 | 2021-09-01 | 2021-11-01 | 4000 | Oversight Committee, CCM members and partners
| Meeting of CCM working groups with national partners (government organizations, NGOs and international organizations) | regularly | regularly | regularly | regularly | 300
| Meeting of CCM working groups with national partners (government organizations, NGOs and international organizations) | regularly | regularly | regularly | regularly | 300
| Electronic approvals involving two PRs and LFA. Materials will be presented that require approval of the CCM. | regularly | regularly | regularly | regularly
Minutes of the meetings are signed and published on CCM web-site | Establishing platforms with MSM, SW, PWID, PLHIV, Transgender communities |  |  |  |  | 600 | Oversight Committee, CCM, MoH, PR, SR
Establishing platforms with MSM community
Establishing platforms with SW community
Establishing platforms with PWID community
Establishing platforms with PLHIV community