## CCM Plan 2022
Agreed December 22, 2021
Minutes 12/22/2021 and 01/26/2022
CCM plan for 2022
Name of the project: | Support to CCM for 2020-2022.
Period: | 2022
Executive partner: | CCM
Results | Activities | Period |  |  |  | Total spending 2022 | Responsible Parties
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Oversight activities completed with participation of all CCM constituencies (documented)
Minutes of the election of the Oversight Committee of the CCM. Supervisory Committee established and functioning | Organize and conduct the election of the oversight committee of the CCM: publishing an announcement, collecting proposals from candidates, announcing the results and distributing the election protocol to members of the CCM | March 31 | X | X | X | 0 | Secretariat of the CCM, Deputy Chairmen of the CCM
Reports with recommendations of the Oversight Committee submitted to CCM members and published on the CCM website | Oversight visits to 3 regions of Kazakhstan (Karaganda, Kostanay regions and Nur-Sultan) will be carried out by 5 specialists in order to determine progress in the implementation of programs in the field of TB and HIV, previously funded by the GFATM. During the meeting with local authorities, special attention will be discussed the plan on state social orders for NGOs. |  |  |  |  | 12200 | Oversight Committee,CCM, MOH, OR, SR.
| Oversight visitt to Karaganda region(4 days): OCAIDS, OCPh, Regional Center for Menthal health, NGO |  | May 17-20
| Oversight visit to Kostanay region (3 days +1 coordination meeting): RCAIDS, OCPh, Regional Center for Menthal health, NGOs |  |  | 22-25 Aug
| Oversight visit to Nur-Sultan (3 days): OCAIDS, CCPh, Regional Center for Menthal health, NGO | April 11-15
Reviewed reports and presentations prepared and submitted to the CCM | Oversight Committee meeting to review PR PUDRs for HIV and TB components based on 2021 results, including review of PR workplans, M&E plans, and results of PR annual audit reports. The report of the Oversight Committee on the results of the review will be presented at the CCM meeting in September 2022. | March14 (Tb spotcheck) |  |  |  | 0 | Oversight Committee, CCM Secretariat and Technical Expert
| Meeting of the Oversight Committee to review PR reports identified from the PUDR review. |  | April (HIV)
| Meeting of the Oversight Committee to review the Principal Recipient's reports on the HIV component, determined from the results of the review of the oversight visits. |  |  | August | November
| Meeting of the Supervisory Committee to review the reports of the Principal Recipient on the TB component, determined based on the results of supervision visits. |  |  |  | November
Minutes of the meetings, Declarations of Conflicts of Interest signed and posted on the CCM website | The meeting of the CCM will be held with the participation of the Ministry of Health, the CCM. The meeting is attended by representatives of two PRs and the LFA. The agenda of the meeting includes: 1) approval of the draft application; 2) Presentation on viral load; 3) presentation of the draft plan for COVID19; 4) Activities to support TB and HIV prevention programs | January 26 | TBD | TBD | TBD | 10000 | Oversight Committee, CCM members and partners
| Meeting of the CCM working groups with national partners (government organizations, NGOs and international organizations) | X | X | X | X
| Meeting of the CCM working groups with national partners (government organizations, NGOs and international organizations) | X | X | X | X
| Electronic approvals involving two ORs and LFAs. Materials will be presented that require coordination with the CCM. | X | X | X | X
The minutes of the meetings are signed and posted on the website of the CCM, the moderators of the meeting are involved | Platform meetings with MSM, SW, PWID, PLHIV, Transgender communities | February 22 |  |  |  | 1000 | Oversight Committee, CCM, MOH, OR, SR.
| Platform meetings with MSM/TGL communities. | X | X | X | X
| Platform meetings with MS communities. | X | X | X | X
| Platform meetings with PWID communities. | X | X | X | X
| Platform meetings with PLHIV communities | X | X | X | X
CCM policy updated to reflect new Global Fund criteria and rules | Working with an international consultant to update the CCM policy. Meetings/Focus groups with CCM members from the non-governmental sector |  | X | X |  | 4000 | Oversight Committee, CCM, MOH, OR, SR.
| Presentation of the first draft of the CCM policy |  |  | X
| CCM policy endorsed at the CCM Meeting |  |  |  | X
Code of Ethics developed, agreed and adopted | Meetings with CCM members from the non-governmental sector, focus groups |  | X |  |  | 1500 | Expert, CCM Secretariat, CCM members
| Presentation of the first draft of the CCM Code of Ethics |  |  | X
| Training for new members of the CCM on the GF platform with the subsequent receipt of a Certificate in compliance with the Code of Ethics |  |  | X
CCM positioning plan developed, agreed and adopted | As part of the Global Fund's pilot project "CCM Evolution", the national consultant will develop a CCM Positioning Plan based on the Global Fund's transition plan for CCM sustainability | x | x | x |  | 4400 | Expert, CCM Secretariat, NGOs, Deputy Chairmen of the CCM
| Meeting with representatives of the relevant Departments of the Ministry of Health and the Ministry of Finance to discuss the draft budget | X | X | X
| Submission of the draft Plan for approval at the CCM meeting |  |  |  | X
The minutes of the meetings are signed and posted on the website of the CCM | Expanded meeting with NGO representatives to discuss program barriers that have arisen due to COVID19 and develop proposals for overcoming the crisis | x | x | x |  | 4401
Report of the international consultant on the results of the training | Training for new members of the CCM on policy issues (qualification criteria for the Global Fund for the CCM, work with voters, gender issues, human rights, work with state bodies) |  |  | X |  | 5800
Support for ZOOM accounts of CCM members | Zoom accounts of old CCM members have been transferred to new CCM members and are functioning |  |  | x |  | 1500 | CCM Secretariat
The CCM website is operational | Support for the CCM website. Timely update of the materials of the CCM website in Russian, Kazakh and English. Domain and hosting support | X | X | X | X | 1000 | CCM Secretariat
Glossary of terms developed | Development of a Glossary of terms that excludes issues of Stigma and discrimination of key populations |  | X |  |  | 400 | Secretariat of the CCM, Deputy Chairmen of the CCM
UBRAF
Module developed and adapted | The training module is designed to enhance the knowledge and skills of parliamentarians on the key components of the Political Declaration on HIV and AIDS: Ending Inequality and Charting the Path to End AIDS by 2030, the new Global AIDS Strategy 2021-2026 End Inequality, End AIDS. |  | X |  |  | 2000 | UNDP project expert
40 representatives of different sectors improved their knowledge and skills | Trainings for 40 participants (20 deputies of maslikhats, parliament, 20 partners from state organizations: ministries and departments of health) aimed at eliminating stigma and discrimination in the legislative process to formulate documents that will meet the needs and requirements. With the involvement of a consultant from Ukraine |  |  | X | X | 10000 | UNDP project expert
Parliamentary hearings on the exclusion of HIV infection from the list of medical contraindications for living in crisis centers and homes for people with disabilities in national legislation. | Meeting for the Ministry of Labor and Social Development, the Ombudsman and the National Center for Human Rights to remove obstacles for PLHIV in providing access to crisis centers: remove HIV infection from the list of medical contraindications for living in crisis centers and homes for people with disabilities in national legislation. |  | X |  |  | 5000 | UNDP project expert
| Consultant's report with recommendations on the analysis of legal documents of the MLSPP |  | X | X | X | 1500
| Final meeting with the participation of responsible parties to discuss the draft proposals for circulation and relevant legal acts |  | X | X | X | 2000
The rules for organizing the work of the regional advisory body have been developed. The program, list, minutes of the demonstration meeting with solutions are developed | Regional coordinating meeting under the Akim of the region in one of the pilot regions to unite the platforms of Maslikhat, UZO, NGOs, KPs - at the local level. Develop work regulations and coordinate with the RCD. |  |  | X |  | 6000 | UNDP project expert and CCM oversight committee
Minutes ogf the meeting developed | Platform meeting with CSOs, Parlamentarians, international organizations on PTAO |  |  | X |  | 5000
Draft Strategic Plan developed | National consultants will develop a draft Strategic Plan |  | X | X |  | 7000 | UNDP project expert
| Training for 30 NGOs on defining Strategic Directions |  | X
| Presentation of the first draft of the Strategy at the workshop |  |  | X
Strategic plan agreed and adapted | A platform of 30 NGOs will agree on a draft Strategic Plan |  |  |  | X | 8000 | UNDP project expert