## OvC_2013
Approved by CCM on November 23, 2012
GFATM Requirement №3 to CCM: Oversight plan for 2013, 2nd Project Year
Project: "Support to Country Coordination Mechanism in 2012-2013"
Purpose of the oversight: Ensure effective and efficient utilization of the resources
Product: Oversight activities are completed and participation of all interested parties is confirmed
No. | Activity | Timeframe Y2 |  |  |  | Responsible party | Comments
|  | 5Q (1) | 6Q (2) | 7Q (3) | 8Q(4)
OIG recommendation 3 А: Engagement of CCM nonmembers in oversight activities. CCM response: Based on the experiences, the CCM initiated a candidature of an Expert from Ministry of Healthcare to participate in implementation of Oversights as a non CCM member. Results showed, it was an adequate way to integrate the scope of recommendations intensively at the national level
1 | Oversight Committee includes representatives of the following organizations: 1) Governmental; 2) international; 3) people living with HIV. Oversight Committee Chair is R. Gailevich, CCM Vice-chair, representative of international organization. |  |  |  |  | CCM | Dates of the activities have to be discussed with the participants.
1а | Group of people living with deseases in order to confirm the participation of previous candidate and/or nominate a new representative from the society into the oversight committee informed through letter from CCM Secretariat. | 31.01. |  |  |  | CCM Oversight Committee, CCM Secretariat
1b | Minutes on results of selection of candidate to oversight committee between people affected by deseases submitted. | 12.02. |  |  |  | Societies and CCM Secretariat
1с | Minutes of CCM meeting on re-approving the Oversight Committee members developed and distributed | 05.03. |  |  |  | CCM Oversight Committee, CCM Secretariat
OGI audit recommendation 3С: Extend CCM oversight to reviews of PUDRs, PR work plans, M&E plans and annual PR audits. CCM response: In order to implement the recommenadtion and follow to the requirements №3 CCM reviewed two PUDRs on results of 2011, PRs annual work plans for 2012 and M&E plan for 2012. Minutes of meeting as of 05.03.2012.
2 | Review of PUDRs on "Tuberculosis" and "HIV" components for 2012, PRs Annual work plans and M&E Plans for 2013. The meeting will be held with participation of LFAs and PRs. | 15.02. |  |  |  | CCM Oversight Committee, СCM, CCM Secretariat, Sh. Ismailov, Manager of project implemenation group, NCTP, B. Assembekov, Head of Department on international donors grants, RCAIDS.
2а | Information on upcoming Oversight Committee meeting, including the meeting agenda and required package documents submitted to PRs and LFAs. | 01.02.
2b | Meeting agenda and PRs preliminary presentations, plans and reports disseminated 1 week prior to the meeting. | 11.02. |  |  |  | CCM Secretariat
2с | Minutes on results of meeting with recommenadtions disseminated and posted on CCM web-site | 22.02. |  |  |  | CCM Secretariat
OGI audit recommendation 3B: Involve technical officers who are not part of the Oversight Committee in oversigh. CCM response: Engagement of technical expert carried out in accordance with the set of qualification requirements which is approved by CCM. CCM Secretariat presented all callected offers in response to the Terms of reference for expert. Suitable candidate to implement CCM oversight functions without rights to vote will be selected by CCM. Outcomes of oversight committee will be discussed with PRs and LFAs and final report presented the CCM. The corresponding report will be disseminated to all interested parties and posted on the CCM web-site.
3 | Three-day field visit to Kyzylorda region to assess progress in implementation of GFATM Grants. Oversight visit will be conducted by 5 specialists selected by CCM according to the requirements of GFATM. GFATM grant sub-recipients (SR): RCAIDS, NCTP. At the end of visit Oversight Committee have a meeting with PRs and LFAs to discuss the results of visit. | 26-29.03. |  |  |  | CCM Oversight Committee, CCM secretariat, PR, West-Кazakhstan region SR | The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members, PRs and LFAs.
3а | ToR for Oversight Committee and expert including the plan and schedule of meetings approved | 05.03. |  |  |  | CCM Oversight Committee, СCM, CCM Secretariat
3b | Individual contract between selected by CCM expert and UNDP signed. | 25.03. |  |  |  | CCM Secretariat, UNDP
3с | Information letter on upcoming visit and copies of Terms of references submitted t to MoH RK, РR and SR | 11.03. |  |  |  | CCM Secretariat
3d | SRs programme and finance reports collected and analysed. | 20.03. |  |  |  | CCM Secretariat, CCM Oversight Committee
3e | Logistical arrangements on purchasing air tickets and payment of travel expenses completed | 25.03. |  |  |  | CCM Secretariat
3f | Oversight Committee and technical expert reports with recommendations are developed and presented to CCM. | 05.04. |  |  |  | CCM Oversight Committee, CCM Secretariat
4 | Three-day field visit to East-Kazakhstan region and Semey city to assess progress in implementation of GFATM Grants. SRs in Oskemen: RCAIDS, NCTP, PF "Кuat", "Answer". SRs in Semey: GCAIDS, PF "Оz tandauyn".Oversight to Oskemen: 23-25.04; to Semey: 26.04. |  | 23-26.04. |  |  | CCM Oversight Committee, CCM Secretariat, PR, SR in East-Kazakhstan region and Semey city | The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members.
4a | ToR for Oversight Committee and expert including the plan and schedule of meetings approved |  | 01.04. |  |  | CCM Oversight Committee, CCM Secretariat
4b | Information letter on upcoming visit and copies of Terms of references submitted to MoH RK, РRs and SRs. |  | 02.04. |  |  | CCM Secretariat
4c | SRs programme and finance reports collected and analysed. |  | 16.04. |  |  | CCM Secretariat, CCM Oversight Committee
4d | Logistical arrangements on purchasing air tickets and payment of travel expenses completed |  | 22.04. |  |  | CCM Secretariat
4e | Reports with recommendations of Oversight Committee and technical expert developed and presented to CCM. |  | 15.05. |  |  | CCM Oversight Committee, CCM Secretariat
5 | Four-day field visit to Pavlodar region, Aksu city to assess progress in implementation of GFATM Grants. SRs in Pavlodar(22-25.05): RCAIDS, NCTP, PF «Аlternativa», PF «Ty ne odin», PF «Gerlita»; SRs in Aksu: (26.05.). |  | 22-26.05. |  |  | CCM Oversight Committee, CCM Secretariat, PR, SR in Pavlodar region and Ekibastuz city | The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members.
5a | ToR for Oversight Committee and expert including the plan and schedule of meetings approved |  | 30.04. |  |  | CCM Oversight Committee, СCM, CCM Secretariat
5b | Information letter on upcoming visit and copies of Terms of references submitted to MoH RK, РRs and SRs. |  | 30.04. |  |  | CCM Secretariat
5c | SRs programme and finance reports collected and analysed. |  | 17.05. |  |  | CCM Secretariat, CCM Oversight Committee
5d | Logistical arrangements on purchasing air tickets and payment of travel expenses completed |  | 21.05. |  |  | CCM Secretariat
5e | Reports with recommendations of oversight committee and technical expert developed and presented to CCM. |  | 03.06. |  |  | CCM Oversight Committee, CCM Secretariat
6 | Five-day field visit to Akmola region and Astana city to assess progress in implementation of GFATM Grants. SRs in Kokshetau: RCAIDS, NCTP; SRs in Astana: city AIDS centre, NCTP, PF "Constanta doc Astana".Oversight to Astana:17-18.06;Kokshetau: 20-21.06. |  | 17-21.06. |  |  | CCM Oversight Committee, CCM Secretariat, PR, SR in Akmola region and Astana city | Territorial distance between the regions allow to combine two visits. The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members.
6a | ToR for Oversight Committee and expert including the plan and schedule of meetings approved |  | 31.05. |  |  | CCM Oversight Committee, СCM, CCM Secretariat
6b | Information letter on upcoming visits and copies of Terms of references submitted to MoH RK, РRs and SRs |  | 31.05. |  |  | CCM Secretariat
6c | SRs programme and finance reports collected and analysed. |  | 12.06. |  |  | CCM Secretariat, CCM Oversight Committee
6d | Logistical arrangements on purchasing air tickets and payment of travel expenses completed |  | 14.06. |  |  | CCM Secretariat
6e | Reports with recommendations of oversight committee and technical expert for two regions developed and presented to CCM. |  | 01.07. |  |  | CCM Secretariat, CCM Oversight Committee
7 | Five-day field visit to Karagandy region,Temirtau and Zhezkazgan to assess progress in implementation of GFATM Grants. SRs in Karagandy (22-23.07): RCAIDS, NCTP, PO«Umit», PО"Sau Urpak";SRs in Temirtau (24-25.07):AIDS&TB centre, PCF"Shapagat"; Zhezkazgan (26.07.) |  |  | 22-26.07. |  | CCM Oversight Committee, CCM Secretariat, PR, SR in Karagandy region, Temirtau and Balkhash cities | The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members, PRs and LFAs.
7a | ToR for Oversight Committee and expert including the plan and schedule of meetings approved |  |  | 03.07. |  | CCM Oversight Committee, СCM, CCM Secretariat
7b | Information on upcoming visits and copies of ToR submitted to MoH RK, РRs and SRs |  |  | 04.07. |  | CCM Secretariat
7c | SRs programme and finance reports collected and analysed. |  |  | 17.07. |  | CCM Secretariat, CCM Oversight Committee
7d | Logistical arrangements on purchasing air tickets and payment of travel expenses completed |  |  | 19.07. |  | CCM Secretariat
7e | Reports with recommendations of oversight committee and technical expert developed and presented to CCM. |  |  | 01.08. |  | CCM Oversight Committee, СCM, CCM Secretariat
8 | Three-day field visit to Almaty oblast to assess progress in implementation of GFATM Grants.SRs:RCAIDS and NCTP, SF«Taldykorgan Regional Employment Fund». |  |  |  | 07-08.10. | CCM Oversight Committee, CCM Secretariat, PR, SR in Almaty region | The dates of oversight committee visits and meetings will be additionally discussed with the oversight committee members, PRs and LFAs.
8a | Terms of reference for oversight Committee and expert including the plan of activities and schedule of meetings with SRs approved |  |  | 16.09. |  | CCM Oversight Committee, СCM, CCM Secretariat
8b | Letters with information on upcoming visits and copies of Terms of references were sent to MoH RK, РRs and SRs |  |  | 17.09. |  | CCM Secretariat
8c | SRs programme and finance reports collected and analysed. |  |  |  | 01.10. | CCM Secretariat, CCM Oversight Committee
8d | Logistical arrangements on purchasing air tickets and payment of travel expenses completed |  |  |  | 06.10. | CCM Secretariat
8e | Reports with recommendations of oversight committee and technical expert developed and presented to CCM. |  |  |  | 22.10. | CCM Secretariat, CCM Oversight Committee, СCM
9 | Analyse of the Reports of SRs of GFAMT grant from Kzylorda oblast. |  |  | 09.08. |  | CCM Oversight Committee, CCM Secretariat, PR, SR in Kzylorda region
9a | Terms of reference for oversight Committee and expert approved |  |  | 02.08.
9b | Letters with information on upcoming oversight committee meeting and copies of ToR submitted to РRs and SRs. |  |  | 02.08.
9c | SRs programme and finance reports collected and analysed. |  |  | 07.08.
9d | Minutes with Oversight Committee and expert recommendations developed and presented |  |  | 26.08.
10 | Analyse the reports of SRs of GFAMT grant from Almaty. SRs: City AIDS centre, "Doctor Li" LTD, PF "Аdali". |  |  | 04.09. |  | CCM Oversight Committee, CCM Secretariat, PR, SR in Almaty city
10a | Terms of reference for Oversight Committee and expert approved |  |  | 26.08.
10b | Letters with information on upcoming Oversight meeting and its ToRs submitted to РRs and SRs. |  |  | 27.08.
10c | SRs programme and finance reports collected and analysed. |  |  | 03.09.
10d | Minutes with Oversight Committee and expert recommendations developed and presented |  |  | 12.09.
11 | Review of the reports with OGI audit recommendations and management plans developed by 2 PRs, SRs and CCM. | 15.02. |  |  |  | CCM Oversight Committee, CCM Secretariat, PR
11a | Terms of reference for Oversight Committee and expert endorsed | 31.02.
11b | Letters with information on upcoming oversight committee meeting and its ToR submitted to РRs and SRs. | 01.02.
11c | Reports and other relevant documentation analysed. | 15.02.
11d | Minutes of oversight committee meeting disseminated | 22.02.
12 | Request for evaluation reports were held by international organizations in 2011-2012. |  |  | 06-10.08. |  | CCM Oversight Committee, CCM Secretariat, PR | Request will be sent to international organizations involved to the HIV/AIDS and TB prevention issues
12a | Terms of reference for oversight Committee and expert approved |  |  | 06.08.
12b | Information to PRs, international organizations on upcoming Oversight Committee meeting and copies of ToR sent. |  |  | 06.08.
12c | Information disseminated to all constituencies&posted on web-site |  |  | 16.08.
12d | Minutes on results of the meeting developed and submited. |  |  | 16.08.