## UPDATED
COUNTRY DIALOGUE PLAN
The goal is to identify the main priorities in HIV / AIDS prevention in the Republic of Kazakhstan with broad involvement of all interested organizations and key persons affected by the disease
Approved by the CCM decision as of 31 January 2020
N/N | Activities | Date | Meeting place/name | Responsible persons | Status
1 | Working meeting of UNAIDS representatives and Principal Recipients of the Global Fund grant with the Global Fund EECA representatives | 14.01.2020 | CCM Secretairat, Kazakh Scientific Center of Dermatology and Infectious Diseases (KSCDID), National Scientific Center of Phthisiopulmonology (NSCP) | Ryssaldy Demeuova | Done
2 | Meeting of CCM members in Almaty with the participation of partners working in the field of HIV/AIDS and tuberculosis, Principal Recipients of the Global Fund grant, representatives of the National Scientific Center of Phthisiopulmonology of the Ministry of Health of the Republic of Kazakhstan (NSCP), Kazakh Scientific Center of Dermatology and Infectious Diseases of the Ministry of Health of the Republic of Kazakhstan (KSCDID) | 15.01.2020 | CCM Secretariat | Ryssaldy Demeuova Ainur Abusseitova | Done
3 | Meeting of the Heads of the National Scientific Center of Phthisiopulmonology of MoH (NSCP), Kazakh Scientific Center of Dermatology and Infectious Diseases of MoH (KSCDID), UNAIDS, CCM Secretariat, Stop TB Partnership, GF Project Implementation Unit to develop the rationale for the program split between HIV and Tuberculosis components | 21.01.2020 | CCM Secretariat, KSCDID, NSCP | Ryssaldy Demeuova, Irina Petrenko | Done
4 | Establishing the Technical working group (TWG) on development of the funding request. Approval of the Country Dialogue Plan | 31.01.2020 | CCM, MoH, KSCDID, UNAIDS, KazUnion PLHIV | Ryssaldy Demeuova, Gabriela Ionascu | Done
5 | Meeting of the CCM TWG on development of the Concept Note and implementation of the Country Dialogue Plan | 07.02.2020 | CCM Secretariat, CCM, TWG | Tatyana Davletgaliyeva | Done
6 | Announcement in the Republican newspaper "Kazakhstanskaya Pravda" (mass media), CCM web site. Creation of electronic mailing list. | 06.02.2020 | CCM Secretariat, CCM | Ryssaldy Demeuova, Ainur Abusseitova | Done
7 | Invitation letter to KSCDID with a request to act as the Principal Recipient of the Global Fund grant for HIV component | after approval of the Global Fund | CCM Secretariat, CCM | Nurali Amanzholov, Alexander Goliusov, Ryssaldy Demeuova
8 | Meeting and in-depth interview with the General Director of the Kazakh Scientific Center of Dermatology and Infectious Diseases on the needs of vulnerable groups of population and PLHIV | after arrival of the Consultant, upon agreement | Baiserkin Bauyrzhan Satzhanovich - General Director of KSCDID | Tatyana Davletgaliyeva
9 | Meeting with representatives of the Global Fund Country Team to discuss preliminary draft CCM decisions on approval of procedures, the main areas of the application and the program split | 30.01.2020 | NSCP, KSCDID, UNAIDS, CCM Vice-Chairs, CCM Secretariat | Alexander Goliusov, Ryssaldy Demeuova | Done
10 | CCM meeting on approval of procedures: 1) approval of the Country Dialogue Plan; 2) establishment of the TWG; 3) consideraion of activities for the new application; 4) approval of the split of funds | 31.01.2020 | CCM Secretariat, CCM Leadership, CCM members, MoH RK | Ryssaldy Demeuova, Ainur Abusseitova | Done
11 | Working meeting of key communities (MSM and transgender people). Following the results of each meeting, proposals will be submitted to the TWG on development of the funding request for inclusion in the national application for the Global Fund | 16.02.2020 | KazUnion PLHIV, UNAIDS | Oxana Ibragimova, Yelena Rastokina, V. Vinogradov, A. Shaikezhanov
12 | Working meeting of key communitites (people who inject drugs). Following the results of each meeting, proposals will be submitted to the TWG on development of the funding request for inclusion in the application | 11.02.2020 | KazUnion PLHIV, UNAIDS, Gennadiy Roshyupkin, CCM secretariat, TWG | Oxana Ibragimova, Yelena Rastokina, Sergey Shetnikov
13 | Working meeting of key communitites (sex workers). | 12.02.2020 |  | Oxana Ibragimova, Natalya Zholnerova
14 | Working meeting of key communitites (PLHIV). | 14.02.2020 |  | Oxana Ibragimova, Natalya Rudokvas
15 | The meeting of CCM working group on gender issues to discuss first draft of report on Ass | 17.02.2020 | CCM working group on gender issues, CCM Secretariat, UNAIDS | Lyudmila Polyakova, Ryssaldy Demeuova, Aliya Bokazhanova
16 | Working meeting of key communitites on HIV/TB | 18.02.2020 | KazUnion PLHIV, NSCP, UNAIDS, CCM Secretariat | Oxana Ibragimova, Ryssaldy Demeuova, Gabriela Ionascu
17 | Negotiations (video-teleconferencing) with the international consultant on development of the funding request and implementation of the Country Dialogue. | upon agreement | KSCDID, PIU | KSCDID , Tatyana Davletgaliyeva
18 | Meeting of the representatives of international organizations (UNAIDS, UNODC, USAID, CDC etc.) and AIDS Centers on consideration of the draft Concept Note (email distribution) | not later that 19.03.2020 | CCM Secretariat, UNAIDS, TWG | Ryssaldy Demeuova, KSCDID , Tatyana Davletgaliyeva, UNAIDS
19 | Collection of proposals in response to the CCM announcement as of February 6, 2020 | 06-06.03.2020 | CCM Secretariat, UNAIDS, TWG | CCM Secretariat
20 | Meeting of the TWG on consideration of proposals of interested parties with the participation of the international consltant | 17.04.2020 | CCM Secretariat, UNAIDS, TWG | CCM Secretariat
21 | The 1st zoom- meeting (visit) of the international consultant with TWG on development of the funding request | 27.04.2020 | CCM secretariat, TWG, PIU, UNAIDS | Gabriela Ionascu, Aliya Bokazhanova, Davletgaliyeva Tatyana, Ryssaldy Demeuova
22 | The 2nd zoom- meeting (visit) of the international consultant with Director of Republican Narcology Center (RNCPZ) to discuss OST in Kazakhstan, progres, gaps and further steps | 05.05.2020 | RNCPZ, PIU, UNODC, UNAIDS, CCM secretariat | Nikolai Negai, Gabriela Ionascu, Gulnur Bolyspayeva, Davletgaliyeva Tatyana, Ryssaldy Demeuova
23 | Sending out of the draft funding request to CCM members by e-mail | 22.05.2020 | CCM Secretariat, UNAIDS, TWG | International consultant, Gabriela Ionascu, Ryssaldy Demeuova
24 | Sending out of the final draft funding request to CCM members for review | not later than 22.05.2020 | CCM Secretariat, TWG | Ryssaldy Demeuova
25 | The 2nd zoom- meeting (visit) of the international consultant with TWG on development of the funding request | 25.05.2020 | CCM secretariat, TWG, PIU, UNAIDS | Gabriela Ionascu, Aliya Bokazhanova, Davletgaliyeva Tatyana, Ryssaldy Demeuova
26 | CCM meeting on approval of the final draft application for Global Fund funding on HIV component | 11.06.2020 | CCM Secretariat, CCM, Ministry of Health RK | CCM Vice-Chairs, MoH, PIU, Ryssaldy Demeuova, Ainur Abusseitova
27 | Submission of Funding Request to the Global Fund Department on Access to Funding | 30.06.2021 | CCM Secretariat, CCM, Ministry of Health RK | CCM Vice-Chairs, MoH, PIU, Ryssaldy Demeuova, Ainur Abusseitova